## Sheet1
2025 TOWNSHIP ROAD CONSTRUCTION PROJECTS
TOWNSHIP | ROAD | FROM | TO | WORK | TOWNSHIP ($) | ICRC ($) | TOTAL ($) | EST | CON | COMP (%) | DATE | Contract Status
Alabaster | [6 empty] | 0
Baldwin | Bischoff Road | Anderson Road | end of certification | Agg Base, HMA, Shoulders | 38259.45 | 16396.91 | 54656.36 | X | X | 100 | 2025-07-01 | Executed
Burleigh | Various Rds | multi | multi | Aggregate Base | 20328 | 8712 | 29040 | X | X | 100 | 2025-04-22 | Executed
Grant | Saginaw Street | Binder Road | Indian Lake Road | HMA, Shoulders | 42667.24 | 18285.96 | 60953.2 | X | X | 100 | 2025-05-22 | Executed
Grant | Imperial Drive | M-55 | E. Branch AuGres River Bridge | HMA, Shoulders | 61553.18 | 26379.94 | 87933.12 | X | X | 0 |  | Executed
Grant | Meadow Road | Sand Lake Road | Chambers Road | Aggregate Base | 8470 | 3630 | 12100 | X | X | 0 |  | Executed
Grant | Youngs Road | M-55 | Meadow Road | Aggregate Base | 6776 | 2904 | 9680 | X | X | 0 |  | Executed
Grant | Birch Street | Boston Road | Sand Lake Road | Tree removal, manholes, pipe | 35574 | 15246 | 50820 | X | X | 0 |  | Executed
Plainfield | Front Street | Long Lake Road | Bliss Street | Aggregate Base | 2567.95 | 1100.55 | 3668.5 | X | X | 100 | 2025-05-01 | Executed
Plainfield | Hale Road | Wickert Road | M-65 | Aggregate Base | 1948.1 | 834.9 | 2783 | X | X | 100 | 2025-05-01 | Executed
Plainfield | Plainfield Ave | Levere Rd | Siegrist Road | HMA, Shoulders | 112977.29 | 48418.84 | 161396.13 | X | X | 100 | 2025-06-26 | Executed
Plainfield | Britt Road | south of Curtis Rd | Misc patching | Aggregate Base | 6198.5 | 2656.5 | 8855 | X | X | 100 | 2025-05-05 | Executed
Plainfield | Maggy's Bay Rd | Lakeside Blvd | Peninsula Ave | Chip Seal | 13887.72 | 5951.88 | 19839.6 | X | X | 100 | 2025-06-25 | Executed
Plainfield | Towerline Road | Wickert Road | M-65 | Exc, Agg Base, HMA, Shoulders | 22127.18 | 9483.08 | 31610.26 | X | X | 100 | 2025-06-19 | Executed
Plainfield | Wickert Road | Towerline Road | M-65 | HMA, Shoulders | 62141.12 | 26631.91 | 88773.03 | X | X | 100 | 2025-06-19 | Executed
Reno | Various Roads | multi | multi | Aggregate Base | 34727 | 14883 | 49610 | X | X | 100 | 2025-04-30 | Executed
Sherman | Turtle Rd | National City Rd | 1 mile east of National City Rd | Mach Grade, HMA, Shoulders | 96149.59 | 41206.97 | 137356.56 | X | X | 100 | 2025-06-12 | Executed
Sherman | Turtle Rd | Rhodes Rd | Sand Lake Rd | Mach Grade, Sand Base, Agg Base, Slope Restoration | 60753 | 26037 | 86790 | X | X | 100 | 2025-06-24 | Executed
Sherman | Turtle Rd | 1 mile east of National City Rd | Sand Lake Rd | Mach Grade, Agg Base, HMA, Shoulders | 137031.36 | 58727.72 | 195759.08 | X | X | 100 | 2025-06-12 | Executed
Sherman | National City Rd | Keystone Rd | Dyer Rd | Mach Grade, HMA, Shoulders | 73912.96 | 73912.96 | 147825.92 | X | X | 100 | 2025-07-02 | Executed
Tawas | McArdle Road | Townline Rd | Meadow Rd | HMA, Shoulders | 96149.59 | 41206.97 | 137356.56 | X | X | 100 | 2025-06-10 | Executed
Tawas | Rempert Road | IRESA | new HMA | HMA, Shoulders | 30925.55 | 13253.81 | 44179.36 | X | X | 100 | 2025-05-22 | Executed
Tawas | Miller Road | Rempert Road | Plank Road | HMA, Shoulders | 16033.9 | 6871.67 | 22905.57 | X | X | 100 | 2025-05-22 | Executed
Tawas | Meadow Road | Lorenz Road | McArdle Road | Mach Grade, Sand Base, Agg Base, Slope Restoration | 215643.89 | 92418.81 | 308062.7 | X | X | 100 | 2025-06-30 | Executed
Tawas | McArdle Road | M-55 | Miller Road | HMA | 100440.03 | 43045.73 | 143485.76 | X | X | 100 | 2025-07-01 | Executed
Wilber | Various Roads | multi | multi | Aggregate Base | 7623 | 3267 | 10890 | X | X | 100 | 2025-04-16 | Executed
Wilber
Total |  |  |  |  | 1304865.6 | 601464.11 | 1906329.71
| Complete | In Progress | AS OF: 7/2/25